## AI Risk Register
Risk ID | Risk Description | Category | Affected AI System | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Treatment Strategy | Mitigation Plan | Owner | Status | Review Date
R001 | Bias in voice recognition leading to higher error rates for non-native English speakers | Bias/Fairness | VoiceGuard | 4 | 4 | 16 | High | Reduce | Implement diverse training dataset expansion; conduct regular bias audits across demographic groups; deploy accent-agnostic models | Sarah Chen | Active | 2026-05-01
R002 | Unauthorized access to voice biometric data stored in cloud infrastructure | Privacy/Security | VoiceGuard | 3 | 5 | 15 | High | Reduce | Implement end-to-end encryption; enforce MFA; conduct quarterly penetration testing; ISO 27001 controls | Marcus Johnson | Active | 2026-04-01
R003 | Service downtime during peak hours affecting emergency voice authentication | Performance/Reliability | VoiceGuard | 3 | 4 | 12 | High | Reduce | Deploy auto-scaling infrastructure; implement multi-region failover; maintain 99.9% SLA monitoring | Priya Patel | Monitoring | 2026-03-02
R004 | AI hallucinations generating incorrect compliance guidance for NIST frameworks | Performance/Reliability | RMF Navigator | 4 | 5 | 20 | Critical | Reduce | Implement RAG with verified NIST documentation; add human-in-the-loop verification; confidence scoring thresholds | Dr. James Wilson | Active | 2026-03-17
R005 | Data breach exposing client compliance assessment data | Privacy/Security | RMF Navigator | 2 | 5 | 10 | Medium | Reduce | AES-256 encryption at rest; role-based access controls; annual third-party security audits; SOC 2 Type II compliance | Marcus Johnson | Active | 2026-05-01
R006 | False negatives on critical hull defects leading to undetected safety issues | Performance/Reliability | VISTA | 3 | 5 | 15 | High | Reduce | Ensemble model approach; mandatory human verification for critical components; continuous model retraining on edge cases | Dr. Elena Rodriguez | Active | 2026-04-01
R007 | Model drift in defect detection due to changing shipyard lighting conditions | Performance/Reliability | VISTA | 4 | 3 | 12 | High | Reduce | Deploy adaptive preprocessing pipeline; weekly performance monitoring; automated retraining triggers | Dr. Elena Rodriguez | Monitoring | 2026-03-02
R008 | Non-compliance with maritime safety regulations due to missed defect reporting | Compliance | VISTA | 2 | 5 | 10 | Medium | Avoid | Implement redundant detection systems; full audit trail logging; integration with US Navy compliance systems | Capt. Michael Torres | Active | 2026-03-17

## Summary
AI Risk Register Summary
Risks by Status
Status | Count
Active | 6
Monitoring | 2
Closed | 0
Risks by Level
Risk Level | Count
Critical | 1
High | 5
Medium | 2
Low | 0
Risks by System
AI System | Total Risks | Critical | High | Medium | Low
VoiceGuard | 3 | 0 | 3 | 0 | 0
RMF Navigator | 2 | 1 | 0 | 1 | 0
VISTA | 3 | 0 | 2 | 1 | 0
Total | 8 | 1 | 5 | 2 | 0